## Bug Tracker
Lopsided Productions Bug Tracker
Last Update: 5/12/2026
Ref # | Bug Name | Bug Summary | Priotity (High, Med, Low) | Reported by | Date Reported | Assigned to | Date Due | Date Resolved | Status (Fixed, Broken, In-Progress) | Comments
BT001 | Start Screen Stretches | After start screen, the room stretches. Rendering needs adjustments | Med | N | 2026-04-16 | J | 2026-04-23 | 2026-04-22 | Fixed
BT002 | Sleep Button | Click navifgation is off. Change events to Left-down. | Med | N | 2026-04-16 | J,N | 2026-04-23 | 2026-04-22 | Fixed
BT003 | Double Tap Speed | Fix (remove) the users ability to quikly double tap the flashlight to get rid of the monster quickly. | Med | J | 2026-04-22 | J | 2026-04-30 |  | In-Progress
BT004 | Game Window | When game is open, the window cannot be resized. |  | T | 2026-04-23 |  |  |  |  | May not be a design bug.
Note on F3: J = Jessica N = Nick T = Tom