## Risks
Lopsided Productions Project Risks
Last Update: 4/16/2026
Ref # | Risk Name | Risk Description | Risk Response Plan | Owner | Probability (1 to 10) | Severity (1 to 10) | Detection (1 to 10) | RPN | Status | Comments
RL01 | Core Gameplay Logic Failure | Sleep meter and threat logic fail to integrate | Test subsystems early in coding and allow corrections as coding continues. Retest in the next round of testing. | J,N,T | 8 | 9 | 1 | 72 | Open
RL02 | Threat Timing Issues | Response window inconsistent | Test validate timers early in coding and allow corrections as coding continues. Retest in the next round of testing. | J,N,T | 7 | 8 | 1 | 56 | Open
RL03 | Game State Errors | Incorrect state transitions | Test centralize state logic early in coding and allow corrections as coding continues. Retest in the next round of testing. | J,N,T | 6 | 9 | 1 | 54 | Open
RL04 | Integration Failure | Subsystems fail to sync | Test integration early in coding and allow corrections as coding continues. Retest in the next round of testing. | J,N,T | 7 | 9 | 1 | 63 | Open
RL05 | Scope Creep | Features exceed scope | Use change control process for any scope creep. It will be determined whether the item must be included in this release. If so, a CR (Change Request) will be completed and then added to the release. If the item does not need to be in the current release, the item will be documented for inclusion in a future release. Scope creep items will be tracked on the Decision Log. | J,N,T | 6 | 7 | 3 | 126 | Open
RL06 | Time Constraint | Insufficient time | Coding, documentation, testing etc., work will be balanced among team. Regular updates on assigned and agreed upon will be provided and will be rebalanced if necessary. | J,N,T | 3 | 8 | 2 | 48 | Open
RL07 | Skill Gaps | Limited GameMaker experience | Team to use tutorials and allocate sufficient time to overcome this risk. | J,N,T | 5 | 7 | 3 | 105 | Open
RL08 | UI Confusion | Players don’t understand UI | Add instructions at the start screen for the user to learn the game rules. | J,N,T | 5 | 6 | 2 | 60 | Open
RL09 | Game Balance | Game too easy/hard | Tune parameters (Time, speed, etc.) to ensure that the game is progressive in level of difficulty. | J,N,T | 3 | 7 | 4 | 84 | Open
RL10 | Late Bugs | Many defects late | Continuous testing will be employed and start at the earliest possible time. Features will be evaluated and tested early in the process to avoid a bottleneck once the coding is complete. | J,N,T | 4 | 8 | 2 | 64 | Open
RL11 | Data Integrity Issues | Invalid values or states | Validate rules throughout the coding process. | J,N,T | 3 | 8 | 4 | 96 | Open
RL12 | Event Handling Conflicts | Timers/input conflict | Structured event logic will be developed and reviewed during the coding process. Results will be documente,d and corrections will be added to the coding tasks. | J,N,T | 5 | 8 | 3 | 120 | Open
RL13 | Environment Failure | Objects don’t affect threats | This risk will be reviewed during the coding and testing process. Results will be documented, and corrections will be added to the coding tasks. | J,N,T | 5 | 7 | 2 | 70 | Open
RL14 | Performance Issues | Low FPS or lag | Test performance early in coding and allow corrections as coding continues. Retest in the next round of testing. | J,N,T | 5 | 8 | 2 | 80 | Open
RL15 | Audio Issues | Audio not synced | Test audio/sound effects early in coding and allow corrections as coding continues. Retest in the next round of testing. | J,N,T | 4 | 6 | 4 | 96 | Open
RL16 | Asset Delay | Missing graphics/audio/sound effects | Use placeholders, assign to individuals, and use due dates to mitigate any impact to coding. | J,N,T | 3 | 6 | 3 | 54 | Open
RL17 | Data Loss | Files corrupted/lost | Use GitHub backups: Team will use GitHub (git pull, git add ., git commit, and git push, etc.) when working on the coding, testing, etc. Any updates are to be pushed to GitHub at the end of the session. | J,N,T | 4 | 9 | 3 | 108 | Open
RL18 | Communication Breakdown | Team miscommunication | Scheduled weekly meetings, Discord, and special coding meetings will be used by each person to keep the team aligned on the progress. | J,N,T | 4 | 7 | 3 | 84 | Open
RL19 | Requirement Misunderstanding | Incorrect implementation | Review SRS on a regulary basis to ensure the build is in alignment. | J,N,T | 3 | 8 | 4 | 96 | Open
RL20 | Incomplete Features | Features not finished | Focus on MVP (Minimum Viable Product) | J,N,T | 5 | 7 | 2 | 70 | Open
RL21 | Traceability Gaps | Requirements not mapped | Maintain RTM (Requirements Tracking Matrix) | J,N,T | 4 | 7 | 3 | 84 | Open
RL22 | Architecture Deviation | Code deviates from SDD | Design will be regularly reviewed and any deviations will be documented as a risk. Deviations will also be tracked on the Decision Log and a Crused if needed. | J,N,T | 5 | 7 | 2 | 70 | Open
Note on F3: J = Jessica N = Nick T = Tom
Note on G3: Probability (P): Likelyhood that the risk is to happen (1 = very unlikely, 10 = very likely)
Note on H3: Severity (S): How bad the impact would be to the project. (1 = minor, 10 = critical)
Note on I3: Detection (D): How difficult it is to detect before it happens. (1 = easy to detect, 10 = very hard to detect)
Note on J3: Risk Priority Number (RPN) = Probability × Severity × Detection

## Risk Quantification Instruction
Probability of Occurance Table
Probability of Occurance | Possible Occurrence Rates | Rank
Very High: occurrence is almost certain | >= 1 in 2 | 10
| 1 in 3 | 9
High: repeated occurences possible | 1 in 8 | 8
| 1 in 20 | 7
Moderate: occassional occurences | 1 in 80 | 6
| 1 in 400 | 5
| 1 in 2,000 | 4
Low: relatively few occurences | 1 in 15,000 | 3
| 1 in 150,000 | 2
Remote: occurrence is unlikely | <= 1 in 1, 500,000 | 1
Severity of the Effect Table
Effect | Criteria: Severity of Effect | Rank
Hazardous - without warning | Project severely impacted, possible cancellation, with no warning | 10
Hazardous - with warning | Project severely impacted, possible cancellation, with warning | 9
Very High | Major impact on project schedule, budget, or performance; may cause severe delays, overruns, or degradation of performance | 8
High | Project schedule, budget, or performance impacted significantly; job can be completed, but customer will be dissatisfied | 7
Moderate | Project schedule, budget, or performance impacted some; customer will be dissatisfied | 6
Low | Project schedule, budget, or performance impacted slightly; customer will be mildly dissatisfied | 5
Very Low | Some impact to project; customer will be aware of impact | 4
Minor | Small impact to project; average customer will be aware of impact | 3
Very Minor | Impact so small that it would be noticed only by a very discriminating customer | 2
Remote: occurrence is unlikely | No effect | 1
Detection Capability
| Detection | Rank
| Absolute Uncertainty | 10
| Very Remote | 9
| Remote | 8
| Very Low | 7
| Low | 6
| Moderate | 5
| Moderately High | 4
| High | 3
| Very High | 2
| Almost Certain | 1

## Issues Log-Required
Lopsided Productions Issues Log
Last Update: 4/16/2026
Ref # | Issue | Owner | Date Reported | Due Date | Date Resolved | Status | Comments | Document Link
IL001
IL002
Note on D3: J = Jessica N = Nick T = Tom

## Bug Tracker
Lopsided Productions Bug Tracker
Last Update: 02/05/2026
Ref # | Bug Name | Bug Summary | Priotity (High, Med, Low) | Reported by | Date Reported | Assigned to | Date Due | Date Resolved | Status (Fixed, Broken, In-Progress) | Comments
BT001 | Start Screen Stretches | After start screen, the room stretches. Rendering needs adjustments | Med | N | 2026-04-16 | J |  |  | In-Progress
BT002 | Sleep Button | Click navifgation is off. Change events to Left-down. | Med | N | 2026-04-16 | J,N |  |  | In-Progress
Note on F3: J = Jessica N = Nick T = Tom