## Issues Quantification
Probability of Occurance Table
Probability of Occurance | Possible Occurrence Rates | Rank
Very High: occurrence is almost certain | >= 1 in 2 | 10
| 1 in 3 | 9
High: repeated occurences possible | 1 in 8 | 8
| 1 in 20 | 7
Moderate: occassional occurences | 1 in 80 | 6
| 1 in 400 | 5
| 1 in 2,000 | 4
Low: relatively few occurences | 1 in 15,000 | 3
| 1 in 150,000 | 2
Remote: occurrence is unlikely | <= 1 in 1, 500,000 | 1
Severity of the Effect Table
Effect | Criteria: Severity of Effect | Rank
Hazardous - without warning | Project severely impacted, possible cancellation, with no warning | 10
Hazardous - with warning | Project severely impacted, possible cancellation, with warning | 9
Very High | Major impact on project schedule, budget, or performance; may cause severe delays, overruns, or degradation of performance | 8
High | Project schedule, budget, or performance impacted significantly; job can be completed, but customer will be dissatisfied | 7
Moderate | Project schedule, budget, or performance impacted some; customer will be dissatisfied | 6
Low | Project schedule, budget, or performance impacted slightly; customer will be mildly dissatisfied | 5
Very Low | Some impact to project; customer will be aware of impact | 4
Minor | Small impact to project; average customer will be aware of impact | 3
Very Minor | Impact so small that it would be noticed only by a very discriminating customer | 2
Remote: occurrence is unlikely | No effect | 1
Detection Capability
| Detection | Rank
| Absolute Uncertainty | 10
| Very Remote | 9
| Remote | 8
| Very Low | 7
| Low | 6
| Moderate | 5
| Moderately High | 4
| High | 3
| Very High | 2
| Almost Certain | 1

## Issues
Lopsided Productions Project Issues
Last Update: 5/12/2026
Ref # | Risk Name | Risk Description | Risk Response Plan | Owner | Probability (1 to 10) | Severity (1 to 10) | Detection (1 to 10) | RPN | Status | Comments
IL01 | Core Gameplay Logic Failure | Sleep meter and threat logic fail to integrate | Test subsystems early in coding and allow corrections as coding continues. Retest in the next round of testing. | Jessica, Nick, Tom | 8 | 9 | 1 | 72 | Closed | Integration of meter and threat tested and complete.
IL02 | Threat Timing Issues | Response window inconsistent | Test validate timers early in coding and allow corrections as coding continues. Retest in the next round of testing. | Jessica, Nick, Tom | 7 | 8 | 1 | 56 | Closed | Tested
IL03 | Game State Errors | Incorrect state transitions | Test centralize state logic early in coding and allow corrections as coding continues. Retest in the next round of testing. | Jessica, Nick, Tom | 6 | 9 | 1 | 54 | Closed | Tested
IL04 | Integration Failure | Subsystems fail to sync | Test integration early in coding and allow corrections as coding continues. Retest in the next round of testing. | Jessica, Nick, Tom | 7 | 9 | 1 | 63 | Closed | Tested
IL05 | Scope Creep | Features exceed scope | Use change control process for any scope creep. It will be determined whether the item must be included in this release. If so, a CR (Change Request) will be completed and then added to the release. If the item does not need to be in the current release, the item will be documented for inclusion in a future release. Scope creep items will be tracked on the Decision Log. | Jessica, Nick, Tom | 6 | 7 | 3 | 126 | Closed | No changes made to project scope.
IL06 | Time Constraint | Insufficient time | Coding, documentation, testing etc., work will be balanced among team. Regular updates on assigned and agreed upon will be provided and will be rebalanced if necessary. | Jessica, Nick, Tom | 3 | 8 | 2 | 48 | Closed
IL07 | Skill Gaps | Limited GameMaker experience | Team to use tutorials and allocate sufficient time to overcome this risk. | Jessica, Nick, Tom | 5 | 7 | 3 | 105 | Closed
IL08 | UI Confusion | Players don’t understand UI | Add instructions at the start screen for the user to learn the game rules. | Jessica, Nick, Tom | 5 | 6 | 2 | 60 | Closed
IL09 | Game Balance | Game too easy/hard | Tune parameters (Time, speed, etc.) to ensure that the game is progressive in level of difficulty. | Jessica, Nick, Tom | 3 | 7 | 4 | 84 | Closed
IL10 | Late Bugs | Many defects late | Continuous testing will be employed and start at the earliest possible time. Features will be evaluated and tested early in the process to avoid a bottleneck once the coding is complete. | Jessica, Nick, Tom | 4 | 8 | 2 | 64 | Closed
IL11 | Data Integrity Issues | Invalid values or states | Validate rules throughout the coding process. | Jessica, Nick, Tom | 3 | 8 | 4 | 96 | Closed
IL12 | Event Handling Conflicts | Timers/input conflict | Structured event logic will be developed and reviewed during the coding process. Results will be documented and corrections will be added to the coding tasks. | Jessica, Nick, Tom | 5 | 8 | 3 | 120 | Closed
IL13 | Environment Failure | Objects don’t affect threats | This risk will be reviewed during the coding and testing process. Results will be documented, and corrections will be added to the coding tasks. | Jessica, Nick, Tom | 5 | 7 | 2 | 70 | Closed
IL14 | Performance Issues | Low FPS or lag | Test performance early in coding and allow corrections as coding continues. Retest in the next round of testing. | Jessica, Nick, Tom | 5 | 8 | 2 | 80 | Closed
IL15 | Audio Issues | Audio not synced | Test audio/sound effects early in coding and allow corrections as coding continues. Retest in the next round of testing. | Jessica, Nick, Tom | 4 | 6 | 4 | 96 | Closed
IL16 | Asset Delay | Missing graphics/audio/sound effects | Use placeholders, assign to individuals, and use due dates to mitigate any impact to coding. | Jessica, Nick, Tom | 3 | 6 | 3 | 54 | Closed
IL17 | Data Loss | Files corrupted/lost | Use GitHub backups: Team will use GitHub (git pull, git add ., git commit, and git push, etc.) when working on the coding, testing, etc. Any updates are to be pushed to GitHub at the end of the session. | Jessica, Nick, Tom | 4 | 9 | 3 | 108 | Closed
IL18 | Communication Breakdown | Team miscommunication | Scheduled weekly meetings, Discord, and special coding meetings will be used by each person to keep the team aligned on the progress. | Jessica, Nick, Tom | 4 | 7 | 3 | 84 | Closed
IL19 | Requirement Misunderstanding | Incorrect implementation | Review SRS on a regulary basis to ensure the build is in alignment. | Jessica, Nick, Tom | 3 | 8 | 4 | 96 | Closed
IL20 | Incomplete Features | Features not finished | Focus on MVP (Minimum Viable Product) | Jessica, Nick, Tom | 5 | 7 | 2 | 70 | Closed
IL21 | Traceability Gaps | Requirements not mapped | Maintain RTM (Requirements Tracking Matrix) | Jessica, Nick, Tom | 4 | 7 | 3 | 84 | Open | Included in test plan
IL22 | Architecture Deviation | Code deviates from SDD | Design will be regularly reviewed and any deviations will be documented as a risk. Deviations will also be tracked on the Decision Log and added if needed. | Jessica, Nick, Tom | 5 | 7 | 2 | 70 | Closed | No deviations noted.
Note on F3: J = Jessica N = Nick T = Tom
Note on G3: Probability (P): Likelyhood that the risk is to happen (1 = very unlikely, 10 = very likely)
Note on H3: Severity (S): How bad the impact would be to the project. (1 = minor, 10 = critical)
Note on I3: Detection (D): How difficult it is to detect before it happens. (1 = easy to detect, 10 = very hard to detect)
Note on J3: Risk Priority Number (RPN) = Probability × Severity × Detection